## Tasks
Week | Category | Task Title
|  |  | Story point | Priority | Task Owner | Status | 2022-06-01 | [29 empty] | 2022-07-01
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Week 1 | Automation | Automate process to copy model results into Excel Sheets using Excel formula | 5 | High | Mook | done | bar: 2022-06-01 6 to 2022-06-01 9
Week 1 | Automation | Automate adjustment for size distributions for Tops | 3 | Medium | Robert | done | bar: 2022-06-01 2; 2022-06-01 6
Week 1 | Model Improvements | QA catboost experiment on online model | 1 | High | Mook | done | bar: 2022-06-01 2
Week 1 | Model Improvements | Test catboost order depth on newest batch and compare with NN results | 3 | High | Robert | done | bar: 2022-06-01 6 to 2022-06-01 7
Week 1 | Code infrastructure | Plan new DFM project design to match data science project seed structure | 2 | High | Robert,Mook | done | bar: 2022-06-01 10
Week 2 | Code infrastructure | Migrate old code base to new project design and make it runnable | 1 | High | Robert | done
Week 2 | Model Improvements | Include postprocessing step include marketing cost cut | 2 | High | Robert | done
Week 2 | Model Improvements | Train Catboost without discount features and compare order depths with latest batches | 8 | High | Robert | in progress
Week 2 | Code infrastructure | Refactor[3]offline_v2_NN_deploy.ipynb to not contain any defining logic but calls to python scripts | 3 | Medium | Robert/Mook | in progress
Week 2 | Code infrastructure | Refactor[3]online_v2_NN_deploy.ipynb to not contain any defining logic but calls to python scripts | 2 | Medium | Robert/Mook | done
Week 2 | Code infrastructure | Refactor [1]online_data_preparation.ipynb to not contain any defining logic but calls to python scripts | 2 | Medium | Robert/Mook
Week 2 | Code infrastructure | Refactor [1]offline_data_preparation.ipynb to not contain any defining logic but calls to python scripts | 3 | Medium | Robert/Mook
| Model Improvements | Add campaign features (mega campaign, campaign, is campaign) - Online [query + transform + deploy] | 5 | Medium
| Model Improvements | Add campaign features (mega campaign, campaign, is campaign) - Offline [query + transform + deploy] | 5 | Medium
| Code infrastructure | Refactor [2]offline_v2_NN_model_training.ipynb | 3 | Low
| Code infrastructure | Refactor [2]online_v2_NN_model_training.ipynb | 3 | Low
| Dashboard | Add accuracy (MAE / avg(demand)) and bias in Looker Dashboard | 2 | Low
| Refactor | Refactor deployment_c_online_sagemaker.py | 2 | Low
| Refactor | Refactor deployment_c_offline_sagemaker.py | 2 | Low
| Automation | update data science tab in master studio budget( excel formula and function in deployement for online model) | 1 | Low
| Refactor | Refactor .sql query for online model | 3 | Low
| Refactor | Refactor .sql query for offline model | 3 | Low
| Refactor | Refactor online_processing_transform.py | 1 | Low
| Refactor | Refactor offline_processing_transform.py | 1 | Low
| Automation | automate lookbook collection name and size in the query | 2 | Low
| Automation | automate campaign/mega campaign in the query - online | 2 | Low
| Automation | automate campaign/mega campaign in the query - offline | 1 | Low
| Model Improvements | Add additional cluster for Singapore in offline model | 5 | Medium
| Model Improvements | Add Product Lifecycle Data | 3 | Medium
| Automation | Write script to automatically create CDC analysis report | 5 | Low
| Model Improvements | Change Category from Camis & Tops to Tops, Camis |  | High
| Refactor | Refactor DU scripts to not contain any hard coded file calls | 1 | Low
| Bug | Traffic dist in offline flow is all nan. (see screenshot)

## TMP
Create dfm model evaluation framework | Status | SP | Adjust model for new categories | Plan Migration for ROS forecasting
Adjust offline data preparation to output clean data indepentend of any model (no train/test split, no lable encoder, all output columns that make sense) | to do |  | Retrain models online/offline for new categories
Adjust Online data preparation to output clean data indepentend of any model (no train/test split, no lable encoder, all output columns that make sense) | done
Create offline model_evaluation script to - Run a model on unseen test set of most recent data - Apply DU strategy for discount columns - Apply size_dist logic same as production Metrics to check: - Accuracy - Bias - Size distribution - CDC Split | to do
Create online model_evaluation script to - Run a model on unseen test set of most recent data - Apply DU strategy for discount columns - Apply size_dist logic same as production Metrics to check: - Accuracy - Bias - Size distribution - CDC Split | to do
Retrain Neural Network on new train set running evaluation framework to get a baseline (online and offline) | to do
Train models (online and offline) on full dataset for deployment | to do

## Milestones Week 1-3
| Milestones week 1-3 | Progress
Week 1 | Largest manual tasks are automated | Done
| Catboost imoprovements are confimred | Done
| new DFM project design is planned | Done
Week 2 | Catboost model is deployed | Delayed
| Code base is migrated to new design enforcing clean coding standards moving forward | Done
| More manual tasks are automated | Done
| Technical dept is reduced | Partially done
Weel 3 | Tracking accuracy and bias in production | Done
| campaign list in the query is more organize and easier to maintain | Delayed
| campaign features are sync with DU strategy and pricing model | Delayed

## Milestones Week 4-X
Milestones week | Progress
No overwrite for online needed
New categories adjusted
30% target for online achieved
Online code architecture refactored (CatBoost)

## SP by week
Week | SUM of | Batch | Total
50
Week 1 | 14 | 2 | 16
Week 2 | 21 | 2 | 23
Grand Total | 85 | 2 | 87